## Scope of Work (in Brief)
Scope of Work in Brief
Sno. | Application | Module | Description
1 | TT | UI Design | Desgin of UI
2 | TT | Master Data Management | Master Data Management Modules including DB Design
3 | TT | Subscription Model | This is for registering companies (if required) (Prototype Model)
4 | TT | Profile Management | Login / Registration / Forgotpassword / profile settings (for each end user)
5 | TT | Cutomer Management | Customer who is getting the service of the truck
6 | TT | Supplier Management | Supplier who will supply the goods.
7 | TT | Truck Management | Truck Owners will register and onboard the trucks, including orders and truck tracking.
8 | TT | Companies Management | for Large Order2
9 | TT | Mobile Application (IOS) | SNO 4,5,6 & 7 of the same
10 | TT | Mobile Application (Andriod) | SNO 4,5,6 & 7 of the same
11 | TT | Reports | Customized reports of all transactions
12 | TT | Email Templates UI & Development | Email Templates
13 | TT | Automated Jobs | Automated jobs
14 | TT | Dashboards | Dashboards for respective users
15 | TT | Maintenance | After deployement

## Time Line Calculation
Sno. | Module | UI Hrs | Dev Hrs | QA Hrs | UAT Hrs | Total
1 | UI Design | 40 |  |  |  | 40
2 | Master Data Management |  | 80 |  |  | 80
3 | Subscription Model |  | 80 | 16 | 8 | 104
4 | Profile Management |  | 120 | 24 | 12 | 156
5 | Cutomer Management |  | 320 | 64 | 32 | 416
6 | Supplier Management |  | 320 | 64 | 32 | 416
7 | Truck Management |  | 320 | 64 | 32 | 416
8 | Companies Management |  | 320 | 64 | 32 | 416
9 | Mobile Application (IOS) |  | 720 | 144 | 72 | 936
10 | Mobile Application (Andriod) |  | 720 | 144 | 72 | 936
11 | Reports |  | 160 | 32 | 16 | 208
12 | Email Templates UI & Development |  | 80 | 16 | 8 | 104
13 | Automated Jobs |  | 120 | 24 | 12 | 156
14 | Dashboards |  | 160 | 32 | 16 | 208
|  | 40 | 3520 | 688 | 344 | 4592
| Disaster management |  |  |  |  | 918.4
| Grand Total Hrs |  |  |  |  | 5510.4
| No. Of Days | 5 | 440 | 86 | 43 | 688.8
| with 1 QA, 4 Developers, 2 Mobile , 1 UI | 5 | 73.3333 | 86 | 43 | 114.8 | 5.2182 | Months

## Cost Management
Sno | Developer | Cost | Months | Total
1 | UI | 25000 | 3 | 75000
2 | .Net Deveoper (Architect & DB Design) | 50000 | 6 | 300000
3 | .Net Deveoper 1 | 30000 | 6 | 180000
4 | .Net Deveoper 2 | 30000 | 6 | 180000
5 | .Net developer 3 | 30000 | 6 | 180000
6 | Mobile Developer 1 | 40000 | 3 | 120000
7 | Mobile Developer 2 | 40000 | 3 | 120000
9 | Tester | 25000 | 6 | 150000
| Total |  |  | 1305000
Additional for client
Sno | Developer | Cost | Months | Total
1 | Server for DEV, UAT and Production | 3000 | 12 | 36000
2 | Certificates | 1000 | 1 | 1000
3 | Domain Registration | 1100 | 1 | 1100
4 | Maintenance | 15000 | 12 | 180000
0
0
218100