## BDS
EMPIRE HOME TENTATIVE BUILD SCHEDULE
SNO | Module | Tasks | Description | Notes | Current Status | Developer | Testing Team | QA ETA | Client ETA
1 | Master Data management | It is a continous process till project ends |  |  | In Progress
2 | User Management | User Roles (Types) | Master data management by Admin | Need to implement in Admin Dashbards / Users section. | Completed |  | Madhuri & Team
3 |  | User Previleges | P | Will be managed by WebAdmin | Completed |  | Madhuri & Team
4 |  | Modules | Modules | will be managed by WebAdmin | Completed |  | Madhuri & Team
5 |  | Previleges, Roles and modules mapping | By Admin to be modified on each role | Wiil be managed by Admin in Masters menu | Not Started | Mahipal Reddy | Madhuri & Team | 2021-10-16 | 2021-10-18
6 |  | Admin/CEO Registration | This user will be added by WebAdmin | NA | Completed |  | Madhuri & Team
7 | Staff Management | Sales, Accountant, HR, Warehouse Keeper etc Registration | These uses will be added by Admin | Will added from Staff-> menu, All Staff list to shown in one screen Add/Edit Staff Screen with predifened fields Enable / Disable functionality to be provided Delete functionality to be provided. After registration an email / sms to be sent to to user with password Forgot password functionality to be provided, Use OTP method to retrieve. | In Progress | Viswesh | Madhuri & Team | 2021-09-28 | 2021-09-30 | 1. relivening
8 | Inventory Management | Inventory Entry/ Update inventory/ list inventory / Stock movement register | Inventory Entry/ Update inventory/ list inventory / Stock movement register | Inventory upload, edit, move stock from warehouse to showroom, showroom to warehouse, necessary documents/images on each transaction, history of stock movement register | In Progress | Mahipal Reddy | Madhuri & Team | 2021-10-03 | 2021-10-05
9 | Dispatch Management | Sale Order Managment, Dispatch management | Sale order management / Warehouse Management / dispatch management | Once product sold, notification will be sent to warehouse keeper, to pack, ship and keep track till delivery / return | Not Started | Mahipal Reddy | Madhuri & Team | 2021-10-29 | 2021-11-01
10 | Cusotmer Management / Sales | Lead generation / Lead enquiry / Convert to customers | Once customer enteres in to show room, sales executive will creates new / selects existing custmers. While negotiating a record in enquiry table to be added. | SE will show the items, selectes the items, creates quotation, appoves by SAles head / CEO based on discount and creates SO and moves to Accounts department | In Progress | Sharukh / Dilip | Madhuri & Team | 2021-11-13 | 2021-11-15
11 | Sales Force Management | Sales Force (Executives) management and their sales performance management | Sales Force (Executives) management and their sales performance management | need to track the performance of the SEs with their daily, monthly, yearly transactions, discounts given, appraisals | Not Started | Vishnu | Madhuri & Team | 2021-12-13 | 2021-12-15
12 | Finance Management | Finance management from all sources | Finance Management from all sources | Includes, Payments from customers, payments to staff and other income and expenditure statments. | Not Started | Mahipal Reddy | Madhuri & Team | 2021-12-13 | 2021-12-15
13 | Staff Management (Payroll) | Staff management including attendance, Payroll | Attendance, payroll | Leaves, Attendance, Salary Advances and approval process | Not Started | Sharukh | Madhuri & Team | 2021-10-16 | 2021-10-18
14 | Email Templates | Email Templates | Email Templates | Need to design email templates for each scenarios | Not Started | Arun / Vishwesh | Madhuri & Team | 2021-10-16 | 2021-10-18
15 | Noifications | Noifications | web notifications | Notifications / alerts to be implemented where ever necessary. | Not Started | Mahipal/Viswesh/dilip/Sharukh | Madhuri & Team | 2021-12-13 | 2021-12-15
16 | Approval Process | Approval system in all modules wherever is necessary | Approval system in all modules wherever is necessary | Approval system to be implemented on some transactions provided by client | Not Started | Mahipal/Viswesh/dilip/Sharukh | Madhuri & Team | 2021-12-13 | 2021-12-15
17 | Dashboards | Super Admin | Super Admin |  | Not Started | Mahipal Reddy | Madhuri & Team | 2022-01-03 | 2022-01-05
18 | Dashboards | Admin (deligates super admin with limited roles), | Admin (deligates super admin with limited roles), |  | Not Started | Vishnu | Madhuri & Team | 2022-01-03 | 2022-01-05
19 | Dashboards | CEO | CEO | Need to show the required information defined by the client for this user | Not Started | Vishnu | Madhuri & Team | 2022-01-03 | 2022-01-05
20 | Dashboards | Sales Head | Sales Head | Need to show the required information defined by the client for this user | Not Started | Vishwesh | Madhuri & Team | 2022-01-03 | 2022-01-05
21 | Dashboards | Sales Executive | Sales Executive | Need to show the required information defined by the client for this user | Not Started | Sharukh | Madhuri & Team | 2022-01-03 | 2022-01-05
22 | Dashboards | Accounts | Accounts | Need to show the required information defined by the client for this user | Not Started | Mahipal/Vishnu | Madhuri & Team | 2022-01-03 | 2022-01-05
23 | Dashboards | Warehouse | Warehouse | Need to show the required information defined by the client for this user | Not Started | Dilip | Madhuri & Team | 2022-01-03 | 2022-01-05

## Tentative Build Dates
SNO | Module | Tasks | Client ETA
1 | Staff Management | Sales, Accountant, HR, Warehouse Keeper etc Registration | 2021-09-30
2 | Inventory Management | Inventory Entry/ Update inventory/ list inventory / Stock movement register | 2021-10-05
3 | Email Templates | Email Templates | 2021-10-10
4 | Staff Management (Payroll) | Staff management including attendance, Payroll | 2021-10-18
5 | User Management | Previleges, Roles and modules mapping | 2021-10-18
6 | Cusotmer Management / Sales | Lead generation / Lead enquiry / Convert to customers | 2021-11-01
7 | Dispatch Management | Sale Order Managment, Dispatch management | 2021-11-15
8 | Sales Force Management | Sales Force (Executives) management and their sales performance management | 2021-12-15
9 | Finance Management | Finance management from all sources | 2021-12-15
10 | Noifications | Noifications | 2021-12-15
11 | Approval Process | Approval system in all modules wherever is necessary | 2021-12-15
12 | Dashboards | Super Admin | 2022-01-05
13 | Dashboards | Admin (deligates super admin with limited roles), | 2022-01-05
14 | Dashboards | CEO | 2022-01-05
15 | Dashboards | Sales Head | 2022-01-05
16 | Dashboards | Sales Executive | 2022-01-05
17 | Dashboards | Accounts | 2022-01-05
18 | Dashboards | Warehouse | 2022-01-05
Hot builds will follows based on client demos and suggestions